## Abstract
RA BILL ABSTRACT
Project Name: | Construction of Loop Road
Client: | TK Toll Road Pvt Ltd
Contractor: | NIP Infra
Work Order No: | WO-2025-001
R.A.Bill No: | RA-07
Bill Period: | 01-007-2025 to 28-007-2025
FINANCIAL SUMMARY
Description | Upto Previous | This Bill
Basic Amount | 600000 | 1200000
SGST 9% | 0 | 108000
CGST 9% | 0 | 108000
Gross Amount | 0 | 1416000
Retention 5% | 0 | 70800
TDS 2% | 0 | 28320
Labour Cess 1% | 0 | 14160
Net Payable | 0 | 1302720

## BOQ
BILL OF QUANTITIES (BOQ)
⚠ IMPORTANT: Do not change the headers on row 8 & 9. Data must start at row 10. Item Code must be numbers.
Item No | Item Code | Description | Unit | Planned Qty | Rate | Planned Amt | Qty Upto Date | Qty Upto Prev | Qty This Bill | Amt Upto Date | Amt Upto Prev | Amt This Bill
1 | 1001 | Earthwork Excavation | CUM | 1000 | 250 | 250000 | 570 | 200 | 370 | 125000 | 50000 | 92500
2 | 1002 | PCC 1:4:8 | CUM | 500 | 4500 | 2250000 | 135 | 0 | 135 | 450000 | 0 | 607500
3 | 1003 | RCC M25 | CUM | 200 | 8000 | 1600000 | 64 | 10 | 54 | 400000 | 80000 | 432000

## 1001
MEASUREMENT SHEET
⚠ Note: Sheet name must exactly match the Item Code from the BOQ sheet (e.g., "1001")
Item 1001: Earthwork Excavation
S.No | Date | RFI No | Description | From | To | Side | Nos | L | B | D | Quantity | IPC | Remarks
1 | 2025-07-14 18:30 | RFI-701 | Excavation LHS | 0 | 100 | LHS | 1 | 100 | 5 | 1 | 500 | 7 | Approved
2 | 2025-07-15 18:30 | RFI-702 | Excavation RHS | 0 | 100 | RHS | 1 | 100 | 5 | 1 | 500 | 7 | Approved

## Non BOQ
NON BOQ / EXTRA ITEMS
⚠ Note: Add any items here that are outside the original scope of the BOQ.
S.No | Description | Unit | Nos | L | B | D | Quantity | Unit Rate | Amount
1 | Extra Soil Shifting | CUM | 1 | 50 | 10 | 2 | 1350 | 150 | 202500